# Karnel Travel Guide – Project Plan & Task Sheet

Oct 30, 2026 · @Ha Pham

A team of three builds the site in 30 days, from 29 Oct to 27 Nov 2026, with each member owning one area end to end.

## 1. Team and Roles

Work is split by feature area so that each member builds their own pages from database to screen, and the workload stays roughly equal.

| Member | Name | Role | Owns |
| --- | --- | --- | --- |
| A | ________ | Team leader, back-end lead | Project plan, Search and Advanced Search, Admin area, status reports, final report and ZIP |
| B | ________ | Database and content lead | ERD, SQL scripts, sample data, Information page and its 5 sub-pages, detail pages |
| C | ________ | Front-end and QA lead | GUI standards, wireframes, shared layout and menu, Home, About Us, Contact Us and Feedback, testing |

All three members write comments in their own code, test their own pages, and write the documents for their area.

## 2. Schedule

project schedule · 6 phases, 3 milestones

Building takes the middle 15 days (6 to 20 Nov); status reports fall on 7 Nov and 17 Nov, and the project is submitted once on 27 Nov.

## 3. Task Sheet

Owners update the Status column as they work; dates assume the 30-day schedule above.

| ID | Phase | Task | Owner | Start | End | Status |
| --- | --- | --- | --- | --- | --- | --- |
| T01 | 1 | Analyse the assignment and list requirements | All | 29 Oct | 29 Oct | Done |
| T02 | 1 | Problem Definition | A | 29 Oct | 30 Oct | Done |
| T03 | 1 | Customer Requirement Specification | A | 29 Oct | 30 Oct | Done |
| T04 | 1 | Choose technology: ASP.NET Core MVC + SQL Server | All | 30 Oct | 30 Oct | Done |
| T05 | 1 | Project Plan and Task Sheet | A | 30 Oct | 31 Oct | In progress |
| T06 | 1 | Create Git repository and folder structure | A | 30 Oct | 31 Oct | Not started |
| T07 | 1 | Collect sample content and images | B | 30 Oct | 05 Nov | Not started |
| T08 | 2 | ERD and table design | B | 01 Nov | 02 Nov | Not started |
| T09 | 2 | SQL create and seed scripts | B | 03 Nov | 05 Nov | Not started |
| T10 | 2 | Sitemap and wireframes | C | 01 Nov | 03 Nov | Not started |
| T11 | 2 | GUI Standards Document | C | 03 Nov | 04 Nov | Not started |
| T12 | 2 | Interface Design Document | C | 04 Nov | 05 Nov | Not started |
| T13 | 2 | Algorithms for search and booking | B | 03 Nov | 05 Nov | Not started |
| T14 | 3 | Set up ASP.NET Core MVC project, EF Core and database connection | A | 06 Nov | 07 Nov | Not started |
| T15 | 3 | Configure hosts file for www.karneltravelguide.com | C | 07 Nov | 07 Nov | Not started |
| T16 | 3 | Status report #1 (STATUS:) | A | 07 Nov | 07 Nov | Not started |
| T17 | 3 | Admin login | B | 08 Nov | 13 Nov | Not started |
| T18 | 3 | Shared layout, menu and footer | C | 06 Nov | 08 Nov | Not started |
| T19 | 3 | Home Page | C | 08 Nov | 10 Nov | Not started |
| T20 | 3 | About Us | C | 10 Nov | 11 Nov | Not started |
| T21 | 3 | Information Page with new places and packages | B | 06 Nov | 08 Nov | Not started |
| T22 | 3 | Tourist Spots and Travel Information pages | B | 08 Nov | 10 Nov | Not started |
| T23 | 3 | Hotel, Restaurant and Resort pages with detail pages | B | 10 Nov | 13 Nov | Not started |
| T24 | 4 | Search tourist spots by type | A | 14 Nov | 15 Nov | Not started |
| T25 | 4 | Search hotels, restaurants and resorts by location, price, quality, quantity, availability | A | 15 Nov | 18 Nov | Not started |
| T26 | 4 | Advanced Search with sorting and paging | A | 18 Nov | 20 Nov | Not started |
| T27 | 4 | Status report #2 (STATUS:) | A | 17 Nov | 17 Nov | Not started |
| T28 | 4 | Contact Us order form with validation | C | 14 Nov | 17 Nov | Not started |
| T29 | 4 | Feedback form | C | 17 Nov | 18 Nov | Not started |
| T30 | 4 | Admin pages: manage data, orders and feedback | B | 14 Nov | 20 Nov | Not started |
| T31 | 5 | Unit Testing Check List and test run | C | 21 Nov | 23 Nov | Not started |
| T32 | 5 | Responsive and browser checks | C | 22 Nov | 23 Nov | Not started |
| T33 | 5 | Bug fixing, each owner in their own area | All | 21 Nov | 24 Nov | Not started |
| T34 | 5 | Code comment review | B | 23 Nov | 24 Nov | Not started |
| T35 | 5 | Project Review and Monitoring Report | A | 23 Nov | 24 Nov | Not started |
| T36 | 6 | Assemble the Project Report | A | 25 Nov | 26 Nov | Not started |
| T37 | 6 | Login credentials and setup guide | B | 25 Nov | 25 Nov | Not started |
| T38 | 6 | Database backup (.bak) and final SQL script | B | 25 Nov | 26 Nov | Not started |
| T39 | 6 | Screenshots and eProjects Feedback Form | C | 25 Nov | 26 Nov | Not started |
| T40 | 6 | Final Check List, ZIP, test on another PC | All | 26 Nov | 27 Nov | Not started |
| T41 | 6 | Submit once with PROJECT SUBMISSION: | A | 27 Nov | 27 Nov | Not started |

Workload: A has 13 tasks, B has 12, C has 12, and 4 are shared by all three.

## 4. Working Rules

- Back up the database and project files every day.

- Each member works on their own Git branch and pushes at the end of every session; A merges into main.

- A short team check-in each day: what was done, what is next, what is blocking.

- B and C send A their progress, screenshots and blockers one day before each status report.

- Questions to the eProjects Team go by email with the subject starting DOUBT:.

- A task is Done only when its page works with real data from the database and its code is commented.